## Sheet1
| Group Members | 86-Praveen Maurya, 89 Jenisha Mehta |  |  | Roll No: | 86,89
| Project Title: | Covid Tracker |  |  | Semester: | Sem II
| Technology Used: | Python flask,heroku,flourish studio, |  |  | Mentor Name: | Rashmi vipat
Sr. No. | Week (Specify date1 - date2) | Activities/ Tasks done in project | Your role/ Responsibility *Specify for each group member | Challenges Faced | Plans for next week | Self Evaluation: 1-5
1 | 5 May- 10 May | Planning | Praveen - selecting platform to develop application, Jenisha - finding Application to handle version control of application | Environment step-up error and required libraries failed to install | Focus on collection of large rest-api for analysis purpose | 4
2 | 11 May - 14 May | Requirement gathering | Praveen- Installation of required Dependancies, Jenisha - Collecting Large amount of Rest-API for analysis purposes | Analysis fail because of improper rest-api found | Implementation of rest-api and Data Preprocessing | 4
3 | 15 May - 23 May | Implementation and Coding | Praveen - Coding to fetch the data, Jenisha - Coding for body design | Coding Error and Improper Output | Focus on Training Program to check no.of cases and vaccine slots | 5
4 | 23 May -25 May | Training | (Both Team Member)- Improving accuracy of code and removing improper REST-API | Error during Execution | Running And Testing the Accuracy of Output | 5
5 | 25 May - 27May | Testing | (Both Team Member) performing multiple scenario to check accuracy of no.of covid patients , vaccination slots | Solving -Unable to Detact the no.of slots |  | 4
Note: - Submit an implementation plan in the form of Gantt/PERT/CPM chart. In case of Gantt chart, give both planned and actual to show deviation from plan.
| Prepared By - |  |  |  |  | Approved By -